## Slide 1
Weeks 1-2: Replicated SMOTE Baseline and Engineered De-biased LLM Pipeline
1. Progress Achieved (Weeks 1-2)
Configured Python environment and replicated the paper’s 'Late-Fusion Logistic Regression' baseline on the 2015-2018 rookie dataset
Final Baseline Metrics: Precision@K: 50.00% , NDCG@K: 51.49%, ROC-AUC: 83.94%, F1-Score: 32.43%
Automated LLM prompting pipeline: PDF extraction (to parse docuemnts) and anonymization (to mitigate ‘look-ahead bias’)
Integrated Gemini API for zero-shot candidate evaluation with structured JSON output
2. Key Challenges & Insights
Baseline Methodology Gap: severely underperformed (NDCG 30.41%) when strictly implementing IPW procedure due to missing institutional classification data. SMOTE oversampling was critical to achieving the paper’s 50% Precision benchmark.
LLM 'Prestige Trap': Initial zero-shot LLMs mirror human, overvaluing elite PhD school prestige. Developed a COT prompt to de-bias the LLM, forcing objective evaluation of true “Research Momentum”.
3. Strategic Next Steps (Weeks 3-5)
Full Batch Run: Evaluate the 2018 cohort via the de-biased CoT pipeline.
Head-to-Head Comparison: Compare LLM accuracy vs. the SMOTE-ML baseline.
Hybrid Integration: Feed LLM-extracted features into XGBoost/LightGBM.
Fine-Tuning: Initiate LLM fine-tuning experiments on the dataset.
Capstone Project: Identifying Research Talent using ML/LLMs | Status Update: May 2026